## Test Cases
TEST CASE ID | MODULE | TEST SCENARIO | TEST CASE | TEST STEPS | EXPECTED RESULT | ACTUAL RESULT | STATUS (PASS/FAIL)
TC-001 | M01 Application Installation and Launch | Verify application installation | Verify that the application can be installed from the official app store | 1. Open Google Play Store 2. Search for 'Aapli Bus VVMT' 3. Tap Install and wait for completion 4. Check the app drawer for the app icon | Application should install successfully without error and the app icon should be available on the device | Not Executed | Not Executed
TC-002 | M01 Application Installation and Launch | Verify application identity | Verify that the app icon and app name are displayed correctly after installation | 1. Install the application 2. Open the device app drawer 3. Observe the app icon and label | Correct app icon and name should be displayed without distortion or truncation | Not Executed | Not Executed
TC-003 | M01 Application Installation and Launch | Verify first launch | Verify that the application launches successfully for the first time after installation | 1. Install the application on a device with no previous install 2. Tap the app icon 3. Observe launch and any permission/onboarding prompts 4. Wait for the home screen | Application should open for the first time, display required prompts correctly and reach the home screen | Not Executed | Not Executed
TC-004 | M01 Application Installation and Launch | Verify splash screen | Verify that the splash screen is displayed correctly during launch | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap the app icon 3. Observe the screen immediately after tapping 4. Verify logo/branding is displayed without distortion | Splash screen should be displayed and transition to the next screen without freezing | Not Executed | Not Executed
TC-005 | M01 Application Installation and Launch | Verify loading behaviour | Verify that a loading indicator or loading state is displayed while the app loads | 1. Tap the app icon 2. Observe the screen between splash and home screen | A loading indicator/state should be visible and the screen should not remain blank | Not Executed | Not Executed
TC-006 | M01 Application Installation and Launch | Verify launch with Internet | Verify that the application launches successfully with an active 4G connection | 1. Ensure 4G data is ON and Wi-Fi is OFF 2. Close the app completely 3. Tap the app icon 4. Wait for the home screen | Application should launch and display the home screen with data loaded | Not Executed | Not Executed
TC-007 | M01 Application Installation and Launch | Verify launch without Internet | Verify application behaviour when launched with no Internet connection | 1. Turn OFF mobile data and Wi-Fi 2. Force stop the app 3. Tap the app icon 4. Observe the screen and any message | Application should either open with available content or show a clear message; exact behaviour: Requirement Confirmation Required | Exploratory observation (formal execution pending): Internet appears necessary during initial app opening. Exact behaviour/message to be recorded during formal execution. | Not Executed
TC-008 | M01 Application Installation and Launch | Verify launch with GPS disabled | Verify application behaviour when launched with device location turned OFF | 1. Turn OFF device location 2. Force stop the app 3. Launch the app 4. Observe prompts and the home screen | Application should launch without crashing and handle disabled location gracefully (prompt or fallback); exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-009 | M01 Application Installation and Launch | Verify app restart | Verify that the app can be closed and reopened normally | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app and reach the home screen 3. Close the app using the Back button/exit 4. Tap the app icon again 5. Observe the home screen | Application should relaunch successfully and display the home screen | Not Executed | Not Executed
TC-010 | M01 Application Installation and Launch | Verify launch after force stop | Verify that the app launches normally after being force stopped | 1. Open Settings > Apps > Aapli Bus VVMT 2. Tap Force Stop 3. Launch the app from the app icon 4. Observe the home screen | Application should launch without crash or error after force stop | Not Executed | Not Executed
TC-011 | M01 Application Installation and Launch | Verify background/foreground behaviour | Verify that the app resumes correctly after being sent to background | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app and open any screen (e.g. map) 3. Press the Home button and wait 1 minute 4. Reopen the app from recent apps 5. Observe the screen state | Application should resume on the same screen without crash, blank screen or data loss | Not Executed | Not Executed
TC-012 | M01 Application Installation and Launch | Verify app after device restart | Verify that the app works normally after rebooting the device | 1. Launch the app and use it briefly 2. Restart the device 3. Launch the app after reboot 4. Verify the home screen and search | Application should launch and function normally after the device restart | Not Executed | Not Executed
TC-013 | M01 Application Installation and Launch | Verify app after update | Verify application behaviour after updating to a newer version (only if an update is available) | 1. Note the current app version and data 2. Update the app from Play Store 3. Launch the app 4. Verify main functions and language setting | Application should launch after update and retain core functionality; if no update is available mark NOT APPLICABLE | Not Executed | Not Executed
TC-014 | M01 Application Installation and Launch | Verify launch stability | Verify that the app does not crash across repeated launches | 1. Launch the app and wait for the home screen 2. Close the app 3. Repeat the launch 5 times 4. Record any crash or error dialog | Application should launch successfully every time without crash or 'App not responding' message | Not Executed | Not Executed
TC-015 | M01 Application Installation and Launch | Verify app freeze/ANR | Verify that the app does not freeze during launch or first interaction | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Tap on a home screen option immediately after it appears 4. Observe responsiveness for 30 seconds | Application should respond to touch without freezing or ANR dialog | Not Executed | Not Executed
TC-016 | M01 Application Installation and Launch | Verify launch interruption | Verify app behaviour when interrupted by an incoming call or notification during launch | 1. Tap the app icon 2. Trigger an incoming call/notification during loading 3. Dismiss the interruption 4. Return to the app | Application should resume without crash and complete loading normally | Not Executed | Not Executed
TC-017 | M02 Application Navigation | Verify home screen | Verify that the home screen displays all main options/sections correctly | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Wait for the home screen to load 4. Observe all visible sections and options | All main sections should be displayed, readable and tappable | Not Executed | Not Executed
TC-018 | M02 Application Navigation | Verify navigation menu | Verify that each navigation menu option opens the correct screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Tap each menu/section option one by one 4. Verify the screen opened 5. Return to home each time | Each option should open its intended screen | Not Executed | Not Executed
TC-019 | M02 Application Navigation | Verify Back button | Verify that the device Back button returns to the previous screen from each main screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a section (e.g. Bus Search) 3. Press the device Back button 4. Observe the screen 5. Repeat for other sections | Back button should return to the previous screen without crash or blank screen | Not Executed | Not Executed
TC-020 | M02 Application Navigation | Verify forward navigation | Verify that moving forward through a flow (search > result > map) works correctly | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Search a bus and select it 4. Open map and then tap a bus icon 5. Observe each transition | Each forward step should open the correct screen without error | Not Executed | Not Executed
TC-021 | M02 Application Navigation | Verify screen transitions | Verify that screen transitions are smooth with no flicker or blank screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Navigate between at least 5 different screens 3. Observe the transitions 4. Note any flicker, delay or blank screen | Transitions should be smooth and complete without visual glitches | Not Executed | Not Executed
TC-022 | M02 Application Navigation | Verify navigation after refresh | Verify that refreshing a screen retains the user on the same screen with correct data | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a screen that supports refresh 3. Perform refresh 4. Observe the screen and data | Screen should refresh and remain on the same screen with valid data | Not Executed | Not Executed
TC-023 | M02 Application Navigation | Verify invalid navigation | Verify behaviour on rapid or repeated taps on navigation options | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Tap a menu option 5 times rapidly 4. Tap two different options quickly 5. Observe the screen | Application should open the screen once without duplicate screens, crash or freeze | Not Executed | Not Executed
TC-024 | M02 Application Navigation | Verify unexpected back navigation | Verify Back button behaviour on the home screen and mid-load | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a screen that takes time to load 3. Press Back while loading 4. Return to home and press Back 5. Observe behaviour | Application should handle Back during loading safely; home screen Back should follow exit behaviour | Not Executed | Not Executed
TC-025 | M02 Application Navigation | Verify exit behaviour | Verify how the application exits from the home screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app and stay on home 3. Press the Back button 4. Observe any exit prompt 5. Confirm exit if prompted | Application should exit cleanly (or show a confirmation); exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-026 | M02 Application Navigation | Verify navigation state after background | Verify that navigation state is retained after the app is backgrounded | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map screen 3. Switch to another app for 30 seconds 4. Return to Aapli Bus VVMT 5. Press Back | App should return to the same screen and Back should follow the previous navigation path | Not Executed | Not Executed
TC-027 | M03 Language / Localization | Verify language change | Verify that the user can change the application language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Open the language selection option 4. Select a different language 5. Observe the screen | Language change option should be available and the selected language should apply | Not Executed | Not Executed
TC-028 | M03 Language / Localization | Verify UI translation | Verify that UI/paragraph content is displayed in the selected language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a non-English language 3. Navigate through the main screens 4. Observe paragraphs and headings | UI and paragraph content should be displayed in the selected language | Exploratory observation (formal execution pending): UI/paragraph content changes when the language is changed. | Not Executed
TC-029 | M03 Language / Localization | Verify buttons translation | Verify that button labels change with the selected language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Change the language 3. Open different screens 4. Observe button labels | Button labels should appear in the selected language without truncation | Not Executed | Not Executed
TC-030 | M03 Language / Localization | Verify menu translation | Verify that menu items are translated after changing language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Change the language 3. Open the navigation menu 4. Observe menu items | Menu items should be displayed in the selected language | Not Executed | Not Executed
TC-031 | M03 Language / Localization | Verify labels translation | Verify that field labels and headings are translated | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Change the language 3. Open search, map and bus stop screens 4. Observe labels and headings | Labels should be displayed in the selected language with correct fit | Not Executed | Not Executed
TC-032 | M03 Language / Localization | Verify error message translation | Verify that error/validation messages appear in the selected language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a non-English language 3. Trigger an error (e.g. search an invalid bus or switch OFF Internet) 4. Read the message | Error messages should appear in the selected language | Not Executed | Not Executed
TC-033 | M03 Language / Localization | Verify search text translation | Verify that search placeholder and hint text change with language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Change the language 3. Open the search screen 4. Observe placeholder, hints and buttons | Search text should be displayed in the selected language | Not Executed | Not Executed
TC-034 | M03 Language / Localization | Verify bus stop information language | Verify the language of bus stop related text after changing language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Change the language 3. Open bus stops 4. Observe stop-related labels and names | Static labels should follow the selected language; bus stop names: Requirement Confirmation Required | Not Executed | Not Executed
TC-035 | M03 Language / Localization | Verify announcement localization | Verify that announcement content changes according to the selected language | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Announcements and note the content 3. Change the application language 4. Reopen Announcements 5. Open an announcement using the eye button 6. Compare content before and after | Announcement content should change to the selected language if localization of announcements is expected; Requirement Confirmation Required | Exploratory observation (formal execution pending): UI/paragraph content changed but announcement content did not appear to change. Whether announcements are expected to be localized is unconfirmed. | Not Executed
TC-036 | M03 Language / Localization | Verify language persistence | Verify that the selected language remains after restarting the app | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a language 3. Close the app completely 4. Relaunch the app 5. Observe the language | Selected language should be retained after restarting the app | Not Executed | Not Executed
TC-037 | M03 Language / Localization | Verify language after device restart | Verify that the selected language persists after device restart | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a language 3. Restart the device 4. Launch the app 5. Observe the language | Selected language should be retained | Not Executed | Not Executed
TC-038 | M03 Language / Localization | Verify repeated language switching | Verify that switching language multiple times does not cause crash or mixed languages | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Switch language 5 times between all available languages 3. Visit home, search and map after each switch 4. Observe text and stability | App should remain stable and show a single consistent language each time | Not Executed | Not Executed
TC-039 | M03 Language / Localization | Verify language switch on active screen | Verify that language change is applied correctly while on a screen (immediate vs after restart) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map screen 3. Change the language from settings 4. Return to the map 5. Observe text | Language should be applied; whether immediate or after restart: Requirement Confirmation Required | Not Executed | Not Executed
TC-040 | M04 Announcements | Verify announcement list | Verify that the announcement list is displayed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Open the Announcements section 4. Observe the list | Available announcements should be listed with readable titles | Not Executed | Not Executed
TC-041 | M04 Announcements | Verify announcement loading | Verify that announcements load without long delay or blank state | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Announcements on 4G 3. Observe loading time and indicator 4. Wait for the list | Announcements should load and a loading indicator should be shown while waiting | Not Executed | Not Executed
TC-042 | M04 Announcements | Verify eye/view button opens announcement | Verify that tapping the eye/view button opens the announcement | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the Announcements section 3. Tap the eye/view button on an announcement 4. Observe the screen | Announcement should open and display its content | Tapping the eye/view button opened the announcement. | PASS
TC-043 | M04 Announcements | Verify announcement content display | Verify that the opened announcement content is complete and readable | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open an announcement using the eye button 3. Read the title and body 4. Scroll if required | Complete content should be displayed with readable text and no overlap | Not Executed | Not Executed
TC-044 | M04 Announcements | Verify close announcement | Verify that an opened announcement can be closed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open an announcement 3. Close it using the close option/Back button 4. Observe the screen | Announcement should close and return to the list | Not Executed | Not Executed
TC-045 | M04 Announcements | Verify multiple announcements | Verify that multiple announcements can be opened one after another | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the first announcement and close it 3. Open the second and third announcements 4. Verify each content | Each announcement should show its own correct content | Not Executed | Not Executed
TC-046 | M04 Announcements | Verify long announcement | Verify the display of a long announcement | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the longest available announcement 3. Scroll to the end 4. Observe text wrapping and cut-offs | Long content should be fully readable with scrolling and no truncation | Not Executed | Not Executed
TC-047 | M04 Announcements | Verify empty announcements | Verify behaviour when no announcements are available (only if reproducible) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Announcements when no announcement exists 3. Observe the screen | An appropriate empty-state message should be displayed rather than a blank screen; if not reproducible mark NOT APPLICABLE | Not Executed | Not Executed
TC-048 | M04 Announcements | Verify announcements without Internet | Verify announcement behaviour after network is turned OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the Announcements list 3. Turn OFF Internet 4. Open an announcement and refresh 5. Observe behaviour | Behaviour (cached content or error message) should be clear and the app should not crash; exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-049 | M04 Announcements | Verify announcement refresh | Verify that announcements can be refreshed and reflect updates | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Announcements 3. Perform refresh (pull-to-refresh/reopen) 4. Observe the list | List should refresh without duplicates or crash | Not Executed | Not Executed
TC-050 | M04 Announcements | Verify announcement persistence after restart | Verify announcements after app restart | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Announcements 3. Close and relaunch the app 4. Open Announcements again | Announcements should be displayed consistently after restart | Not Executed | Not Executed
TC-051 | M05 Bus Search | Verify search by valid bus number | Verify that searching for an existing bus number displays the bus | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter a valid bus number (e.g. 101, 102, 103, 104, 105, 106) 4. Submit the search 5. Observe the result | Bus should be displayed if it exists in the application's current route data | Bus numbers 101-106 were available and found during exploratory testing. | PASS
TC-052 | M05 Bus Search | Verify search by invalid bus number | Verify the message for a non-existent bus number | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter a clearly invalid number (e.g. 99999) 4. Submit the search 5. Observe the message | A 'no result' message should be displayed; app should not crash | Not Executed | Not Executed
TC-053 | M05 Bus Search | Verify search for bus 107 | Verify search result for bus number 107 | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter 107 4. Submit the search 5. Observe the result 6. Check official route data for bus 107 | Bus should be displayed if it exists in the application's current route data | Exploratory observation (formal execution pending): Bus 107 was not found. Not classified as a defect until 107 is confirmed as an officially supported route. | Not Executed
TC-054 | M05 Bus Search | Verify empty search | Verify behaviour when search is submitted with empty input | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Leave the field empty 4. Tap search/submit 5. Observe behaviour | No crash; message or default list should be displayed; exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-055 | M05 Bus Search | Verify partial bus number | Verify search with a partial bus number | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter '10' 4. Observe suggestions/results 5. Select one result | Matching buses should be listed or suggested; exact matching rule: Requirement Confirmation Required | Not Executed | Not Executed
TC-056 | M05 Bus Search | Verify alphabetic input | Verify search with alphabetic input | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter 'ABC' 4. Submit the search 5. Observe the response | Application should show no results or a validation message without crashing | Not Executed | Not Executed
TC-057 | M05 Bus Search | Verify special characters | Verify search with special characters | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter '@#$%' 4. Submit the search 5. Observe the response | Application should handle input safely without crash or incorrect results | Not Executed | Not Executed
TC-058 | M05 Bus Search | Verify spaces in search | Verify search with leading/trailing/only spaces | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter ' 102 ' with spaces 4. Submit the search 5. Enter only spaces and submit | Leading/trailing spaces should be handled; space-only input should not crash; exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-059 | M05 Bus Search | Verify very long input | Verify search with a very long text string | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Paste 100+ characters 4. Submit the search 5. Observe response | Application should handle long input without crash or UI break | Not Executed | Not Executed
TC-060 | M05 Bus Search | Verify multiple results | Verify behaviour when multiple buses match | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Enter a prefix expected to match several buses (e.g. '10') 4. Observe the list 5. Scroll through results | All matching buses should be listed correctly with no duplicates | Not Executed | Not Executed
TC-061 | M05 Bus Search | Verify bus stop search | Verify that a bus stop can be searched by name | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the search section 3. Enter a valid bus stop name (e.g. Nalasopara Phata) 4. Observe the results | Matching bus stops should be listed | Bus stops could be searched during exploratory testing. | PASS
TC-062 | M05 Bus Search | Verify search result selection | Verify that selecting a search result opens the correct details | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Search a valid bus 3. Tap the result 4. Observe the opened screen | Selected result should open its correct details/map | Not Executed | Not Executed
TC-063 | M05 Bus Search | Verify clear search | Verify that the search field can be cleared | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enter text in the search field 3. Tap the clear (X) option or delete text 4. Observe the field and results | Field should clear and the result list should reset | Not Executed | Not Executed
TC-064 | M05 Bus Search | Verify search after network loss | Verify search behaviour when Internet is lost | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Turn OFF Internet 4. Search a bus number 5. Observe behaviour | Result or error message should be clear and app should not crash; exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-065 | M05 Bus Search | Verify search with GPS disabled | Verify that search works when device location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open Bus Search 4. Search a valid bus number 5. Observe the result | Search should work as designed without location; whether GPS is required: Requirement Confirmation Required | Not Executed | Not Executed
TC-066 | M06 Bus Details and Map | Verify selecting a bus opens map | Verify that selecting a bus (e.g. Bus 102) from search opens the map | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Bus Search 3. Search Bus 102 4. Select the bus from the result 5. Observe the screen | Map should open for the selected bus | Searched Bus 102 and selected it; the map opened. | PASS
TC-067 | M06 Bus Details and Map | Verify map loading | Verify that the map loads completely | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a bus to open the map 3. Observe the map tiles and route 4. Wait until fully loaded | Map tiles, route and bus markers should load without blank areas | Not Executed | Not Executed
TC-068 | M06 Bus Details and Map | Verify bus icon display | Verify that bus icons are visible on the route | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for a bus (e.g. 102) 3. Observe the route 4. Look for bus icons | Bus icons should be visible on the route | Bus icons were visible on the route. | PASS
TC-069 | M06 Bus Details and Map | Verify bus number/details on icon tap | Verify that tapping a bus icon displays bus number/details | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for Bus 102 3. Tap a bus icon 4. Observe the details shown | Bus number/details should be displayed | Tapping a bus icon displayed the bus number/details. | PASS
TC-070 | M06 Bus Details and Map | Verify bus number display | Verify that the bus number shown matches the searched bus | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Search Bus 102 3. Open the map 4. Compare the number on the screen/icon with 102 | Displayed bus number should match the selected bus | Not Executed | Not Executed
TC-071 | M06 Bus Details and Map | Verify route information | Verify that route information (start/end/stops) is displayed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for a bus 3. Observe the route information panel 4. Verify start and end | Route information should be displayed and consistent with route data | Not Executed | Not Executed
TC-072 | M06 Bus Details and Map | Verify bus location on route | Verify that bus icons lie on the displayed route | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Zoom to a bus icon 4. Compare position with the route line | Bus icon should be positioned on/near the route | Not Executed | Not Executed
TC-073 | M06 Bus Details and Map | Verify map zoom | Verify map zoom in and zoom out | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Use pinch zoom in and zoom out 4. Use double-tap 5. Observe the map | Map should zoom smoothly in both directions | Not Executed | Not Executed
TC-074 | M06 Bus Details and Map | Verify map movement | Verify map panning | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Drag the map in all directions 4. Observe the map | Map should move smoothly and tiles should load | Not Executed | Not Executed
TC-075 | M06 Bus Details and Map | Verify map refresh | Verify map/bus data refresh | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Perform refresh (or wait for auto refresh) 4. Observe bus positions | Bus data should refresh without map reset or crash | Not Executed | Not Executed
TC-076 | M06 Bus Details and Map | Verify multiple buses on map | Verify display of multiple buses on the same route | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a route with more than one bus 3. Observe the icons 4. Tap each icon | Each bus should be displayed with its own number/details | Not Executed | Not Executed
TC-077 | M06 Bus Details and Map | Verify bus stops on map | Verify that bus stops are displayed along the route | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for a bus 3. Observe the bus stop markers 4. Tap a bus stop | Bus stops should be displayed and show details on tap | Not Executed | Not Executed
TC-078 | M06 Bus Details and Map | Verify map with GPS disabled | Verify map behaviour when device location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open the map for a bus 4. Observe the map and buses | Map should open; behaviour regarding user location: Requirement Confirmation Required | Not Executed | Not Executed
TC-079 | M06 Bus Details and Map | Verify map with network disabled | Verify map behaviour when Internet is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Turn OFF Internet 4. Pan/zoom and refresh 5. Observe behaviour | App should not crash; behaviour of map/bus data: Requirement Confirmation Required | Not Executed | Not Executed
TC-080 | M06 Bus Details and Map | Verify back from map | Verify Back navigation from the map | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Press Back 4. Observe the screen | App should return to the previous screen without crash | Not Executed | Not Executed
TC-081 | M07 Live Bus Tracking | Verify bus location display | Verify that live bus location is shown on the map | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for a running bus 3. Observe the bus position 4. Compare with the expected route | Bus location should be displayed on the map | Not Executed | Not Executed
TC-082 | M07 Live Bus Tracking | Verify bus movement | Verify that a bus icon moves over time | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Observe a bus icon for 2-3 minutes 4. Note position changes | Bus position should update as the bus moves; update behaviour: Requirement Confirmation Required | Exploratory observation (formal execution pending): A yellow bus appeared to be moving. Not verified against real-world movement. | Not Executed
TC-083 | M07 Live Bus Tracking | Verify bus status | Verify that bus status information is shown | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap a bus icon 3. Read the status/details 4. Note available fields | Bus status information should be consistent with the application's defined statuses; Requirement Confirmation Required | Not Executed | Not Executed
TC-084 | M07 Live Bus Tracking | Verify bus icon consistency | Verify consistent icon appearance for all buses | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map with multiple buses 3. Compare icon shape/size 4. Zoom in/out | Icons should be consistent and clearly visible | Not Executed | Not Executed
TC-085 | M07 Live Bus Tracking | Verify bus colour indicators | Verify that the bus colour indicator corresponds to the status defined by the application | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Observe bus icons (green/yellow observed) 4. Tap each coloured bus 5. Compare with in-app legend/help or official documentation | Verify that the bus color indicator corresponds to the status defined by the application; Requirement Confirmation Required | Exploratory observation (formal execution pending): Green and yellow bus indicators were observed. Meaning not documented/confirmed. | Not Executed
TC-086 | M07 Live Bus Tracking | Verify tracking refresh | Verify refresh behaviour of tracking data | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Perform manual refresh 4. Observe icon updates | Data should refresh and positions update | Not Executed | Not Executed
TC-087 | M07 Live Bus Tracking | Verify location update interval | Verify how frequently bus locations update | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Note position and time of a bus 4. Re-check every 30 seconds for 3 minutes | Positions should update periodically; interval: Requirement Confirmation Required | Not Executed | Not Executed
TC-088 | M07 Live Bus Tracking | Verify multiple buses tracking | Verify simultaneous tracking of multiple buses | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a route with multiple buses 3. Observe all icons for 2 minutes 4. Tap each icon | All buses should be tracked without icon overlap issues or lag | Not Executed | Not Executed
TC-089 | M07 Live Bus Tracking | Verify tracking with GPS disabled | Verify live tracking when device location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open the map 4. Observe bus icons and movement for 2 minutes | Tracking behaviour should be recorded; whether tracking depends on user GPS: Requirement Confirmation Required | Not Executed | Not Executed
TC-090 | M07 Live Bus Tracking | Verify tracking with network disabled | Verify tracking behaviour after Internet is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map showing buses 3. Turn OFF Internet 4. Observe icons for 2 minutes 5. Turn ON Internet and observe | Behaviour (frozen/cached/updating) should be identified; recovery on reconnect should work; Requirement Confirmation Required | Not Executed | Not Executed
TC-091 | M07 Live Bus Tracking | Verify delayed bus | Verify how a delayed bus is represented (if observable) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Look for a bus with delay/idle indication 4. Tap the bus 5. Compare with timing information | Delayed bus information should be clear; indicator definition: Requirement Confirmation Required | Not Executed | Not Executed
TC-092 | M07 Live Bus Tracking | Verify bus unavailable | Verify behaviour when no bus is currently running on a route | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a route with no active bus 3. Open the map 4. Observe the screen | An appropriate message or empty state should be shown instead of a blank map; if not reproducible mark NOT APPLICABLE | Not Executed | Not Executed
TC-093 | M07 Live Bus Tracking | Verify route change | Verify behaviour when switching from one bus/route to another | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for Bus 102 3. Go back and select Bus 103 4. Observe route and icons | Previous route data should be cleared and new route displayed correctly | Not Executed | Not Executed
TC-094 | M07 Live Bus Tracking | Verify stale data | Verify whether stale data is indicated when updates stop | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Turn OFF Internet for 5 minutes 4. Observe icons and any timestamp/warning | Stale data should be indicated or clearly identifiable; Requirement Confirmation Required | Not Executed | Not Executed
TC-095 | M08 GPS / Location | Verify location permission allowed | Verify behaviour when location permission is allowed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Fresh install or clear permissions 3. Launch the app 4. Allow location permission 5. Open the map/nearby features | App should use location and show current location/nearby data | Not Executed | Not Executed
TC-096 | M08 GPS / Location | Verify location permission denied | Verify behaviour when location permission is denied | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Reset permissions 3. Launch the app 4. Deny location permission 5. Use search/map/nearby features | App should not crash and should explain or provide fallback | Not Executed | Not Executed
TC-097 | M08 GPS / Location | Verify location disabled | Verify behaviour when device location is turned OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open the app 4. Open map and nearby features 5. Observe prompts | App should handle it gracefully (prompt/fallback); exact behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-098 | M08 GPS / Location | Verify location enabled | Verify behaviour when device location is turned ON | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn ON device location 3. Open the app 4. Open map and nearby features | Location-based features should work correctly | Not Executed | Not Executed
TC-099 | M08 GPS / Location | Verify first permission request | Verify that the first permission request is clear and displayed once | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Install fresh 3. Launch the app 4. Observe the permission dialog 5. Select an option | Permission request should be clear and not repeat unnecessarily | Not Executed | Not Executed
TC-100 | M08 GPS / Location | Verify permission revoked while running | Verify behaviour when permission is revoked from settings while the app is in background | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use the app with permission allowed 3. Revoke location permission from Settings 4. Return to the app 5. Use location features | App should not crash and should re-request or show a message | Not Executed | Not Executed
TC-101 | M08 GPS / Location | Verify app after permission change | Verify the app after changing permission from Deny to Allow | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Deny permission and use the app 3. Enable permission from Settings 4. Return to the app 5. Use location features | Location features should work after permission is allowed | Not Executed | Not Executed
TC-102 | M08 GPS / Location | Verify current location | Verify that the user's current location is displayed correctly | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable location 3. Open the map 4. Locate the current-location marker 5. Compare with actual position | Current location marker should be displayed near the actual position | Not Executed | Not Executed
TC-103 | M08 GPS / Location | Verify nearby bus stops | Verify that nearby bus stops are listed based on location | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable location 3. Open nearby bus stops 4. Compare listed stops with surroundings | Nearby stops should be listed and relevant to the current location | Not Executed | Not Executed
TC-104 | M08 GPS / Location | Verify nearby buses | Verify that nearby buses are shown (if feature exists) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable location 3. Open nearby buses/map 4. Observe listed buses | Nearby buses should be shown; if the feature is absent mark NOT APPLICABLE | Not Executed | Not Executed
TC-105 | M08 GPS / Location | Verify location accuracy | Verify accuracy of the displayed user location | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable high-accuracy location 3. Open the map outdoors 4. Compare marker with a known landmark | Marker should reasonably match the actual position; accuracy tolerance: Requirement Confirmation Required | Not Executed | Not Executed
TC-106 | M08 GPS / Location | Verify location refresh | Verify that location updates when the user moves | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Move to another location or simulate movement 4. Observe the marker update | Marker should update with the new location | Not Executed | Not Executed
TC-107 | M08 GPS / Location | Verify buses visible with location OFF - previously loaded data | Verify whether previously loaded bus data remains visible after turning location OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map with buses loaded 3. Turn OFF device location 4. Observe icons | Behaviour should be recorded; previously loaded data may remain visible; Requirement Confirmation Required | Exploratory observation (formal execution pending): Buses can still be visible when device location is OFF. Not yet determined whether this is previously loaded data or live data. | Not Executed
TC-108 | M08 GPS / Location | Verify live data updates with location OFF | Verify whether live bus data continues updating when location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open the map 4. Observe bus positions for 3 minutes | Updates should continue only if tracking does not depend on user GPS; Requirement Confirmation Required | Not Executed | Not Executed
TC-109 | M08 GPS / Location | Verify current location feature with location OFF | Verify user current location feature when location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Tap the current-location option 4. Observe prompt/behaviour | App should prompt to enable location or show a clear message | Not Executed | Not Executed
TC-110 | M08 GPS / Location | Verify nearby functionality with location OFF | Verify nearby bus stops/buses when location is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open nearby bus stops 4. Observe the result | Nearby feature should show a message/fallback and not crash; Requirement Confirmation Required | Not Executed | Not Executed
TC-111 | M09 Location / Area Name Accuracy | Verify accuracy of displayed location/area name | Verify accuracy of displayed location/area name | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable location at the test spot 3. Open the screen that shows the area name 4. Note the displayed name (e.g. 'Polhar Highway Rasta') 5. Compare with the official name from Google Maps/VVMT sources | Displayed area name should match the officially verified name of the location; official name needs verification before conclusion | Exploratory observation (formal execution pending): App displayed 'Polhar Highway Rasta'; tester expected a possibly more accurate name such as 'Pelhar / Vasai Phata'. Official name not yet verified. | Not Executed
TC-112 | M09 Location / Area Name Accuracy | Verify location name against official source | Verify the displayed name against at least two independent sources | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Record the app's displayed name 3. Check Google Maps and official VVMT stop list 4. Record both names 5. Compare | Differences should be documented; defect only if the app's name is confirmed incorrect | Not Executed | Not Executed
TC-113 | M09 Location / Area Name Accuracy | Verify location name consistency across screens | Verify the same location is named consistently across screens | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Note the area name on the map 3. Check the same place in search, bus stop list and route details 4. Compare names | Name should be consistent across screens | Not Executed | Not Executed
TC-114 | M09 Location / Area Name Accuracy | Verify location name after refresh/movement | Verify the area name updates correctly after refresh or movement | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Note the current area name 3. Refresh or move to another area 4. Observe the updated name | Area name should update to match the new location | Not Executed | Not Executed
TC-115 | M10 Bus Stops | Verify bus stop search | Verify that bus stops can be searched by name | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open bus stop search 3. Enter a valid stop name 4. Observe the results | Matching stops should be listed | Not Executed | Not Executed
TC-116 | M10 Bus Stops | Verify bus stop selection | Verify that a bus stop can be selected from the result list | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Search a bus stop 3. Tap a result 4. Observe the screen | Selected stop should open | Not Executed | Not Executed
TC-117 | M10 Bus Stops | Verify Nalasopara Phata bus stop opens correctly | Verify that selecting 'Nalasopara Phata' displays bus stop details | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open bus stop search 3. Search or select 'Nalasopara Phata' 4. Observe the screen that opens 5. Wait 30 seconds 6. Retry 3 times and note result | Relevant bus stop details should be displayed | Exploratory observation (formal execution pending): Screen opens but appears blank. Reproduction to be confirmed during formal execution. | Not Executed
TC-118 | M10 Bus Stops | Verify bus stop details | Verify the details shown for a bus stop | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a bus stop that loads 3. Observe name, routes and timings 4. Verify against known data | Bus stop name and relevant routes/details should be displayed | Not Executed | Not Executed
TC-119 | M10 Bus Stops | Verify nearby bus stops | Verify nearby bus stops list | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable location 3. Open the nearby bus stops section 4. Observe the list | Nearby stops should be displayed relevant to the location | Not Executed | Not Executed
TC-120 | M10 Bus Stops | Verify 'See All' meaning | Verify whether 'See All' shows all bus stops or only nearby bus stops | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open nearby bus stops 3. Tap See All 4. Observe the list and heading 5. Compare against the full bus stop list 6. Check help/official documentation | 'See All' behaviour should match the application's defined meaning (all stops vs all nearby stops); Requirement Confirmation Required | Exploratory observation (formal execution pending): 'See All' shows nearby bus stops. Intended meaning not confirmed. | Not Executed
TC-121 | M10 Bus Stops | Verify 'See All' list completeness | Verify that the 'See All' list loads fully and scrolls | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap See All 3. Scroll to the end 4. Observe count and duplicates | List should load fully with no duplicates or missing items | Not Executed | Not Executed
TC-122 | M10 Bus Stops | Verify bus stop map | Verify that the bus stop location is shown on the map | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a bus stop 3. Open its map view 4. Verify the marker location | Stop marker should be shown at the correct location | Not Executed | Not Executed
TC-123 | M10 Bus Stops | Verify bus routes at stop | Verify that bus routes passing through a stop are displayed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a bus stop 3. Observe the list of routes/buses 4. Tap a route | Relevant routes should be displayed and open correctly | Not Executed | Not Executed
TC-124 | M10 Bus Stops | Verify other bus stops open correctly | Verify that other bus stops open details (compare with Nalasopara Phata) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open 5 different bus stops 3. Observe each screen 4. Record any blank screens | Each bus stop should open with its details | Not Executed | Not Executed
TC-125 | M10 Bus Stops | Verify empty bus stop | Verify a stop with no upcoming bus information | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a stop expected to have no buses 3. Observe the screen | An appropriate empty-state message should be displayed instead of a blank screen | Not Executed | Not Executed
TC-126 | M10 Bus Stops | Verify invalid bus stop | Verify search for a non-existent bus stop | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open bus stop search 3. Enter 'XYZ123' 4. Observe the result | No-result message should be displayed without crash | Not Executed | Not Executed
TC-127 | M10 Bus Stops | Verify bus stop with GPS disabled | Verify bus stop functionality with location OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF device location 3. Open bus stops 4. Search and open a stop 5. Observe | Searching/opening stops should work; nearby feature behaviour: Requirement Confirmation Required | Not Executed | Not Executed
TC-128 | M10 Bus Stops | Verify bus stop with network disabled | Verify bus stop screen when Internet is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a bus stop 3. Turn OFF Internet 4. Refresh or reopen 5. Observe | App should not crash; message or cached content; Requirement Confirmation Required | Not Executed | Not Executed
TC-129 | M10 Bus Stops | Verify bus stop refresh | Verify refresh on the bus stop screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a bus stop 3. Perform refresh 4. Observe data | Data should refresh without error | Not Executed | Not Executed
TC-130 | M10 Bus Stops | Verify Back navigation from bus stop | Verify Back behaviour from stop details and See All | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open See All 3. Open a stop 4. Press Back twice 5. Observe screens | Back should return correctly step by step | Not Executed | Not Executed
TC-131 | M11 Journey Planning | Verify journey planning availability | Verify whether a journey planning feature exists in the application | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Look for a journey planner/route planner option 4. Open it if present | If the feature exists proceed; otherwise mark all journey cases NOT APPLICABLE | Not Executed | Not Executed
TC-132 | M11 Journey Planning | Verify source selection | Verify that a source can be selected | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open journey planning 3. Tap the source field 4. Search and select a source stop | Selected source should be displayed | Not Executed | Not Executed
TC-133 | M11 Journey Planning | Verify destination selection | Verify that a destination can be selected | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open journey planning 3. Tap the destination field 4. Select a destination | Selected destination should be displayed | Not Executed | Not Executed
TC-134 | M11 Journey Planning | Verify same source and destination | Verify behaviour when both are the same | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select the same stop as source and destination 3. Tap search | Validation message should be displayed or no route shown | Not Executed | Not Executed
TC-135 | M11 Journey Planning | Verify valid route | Verify route result for a valid source and destination | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select valid source and destination 3. Search routes 4. Observe the result | Valid route(s) should be displayed | Not Executed | Not Executed
TC-136 | M11 Journey Planning | Verify invalid route | Verify behaviour for invalid input | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enter an invalid source/destination 3. Tap search 4. Observe | Validation/no-result message without crash | Not Executed | Not Executed
TC-137 | M11 Journey Planning | Verify no route available | Verify the message when no route exists | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select two stops with no direct route 3. Search 4. Observe | A clear no-route message should be displayed | Not Executed | Not Executed
TC-138 | M11 Journey Planning | Verify multiple routes | Verify that multiple route options are displayed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a pair with several options 3. Search 4. Compare the options | Multiple routes should be listed clearly | Not Executed | Not Executed
TC-139 | M11 Journey Planning | Verify bus number in route | Verify the bus number shown in route results | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Plan a journey 3. Open a route 4. Verify bus numbers | Displayed bus numbers should be valid and correct | Not Executed | Not Executed
TC-140 | M11 Journey Planning | Verify bus stops in route | Verify the bus stops listed in route details | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open route details 3. Check the sequence of stops | Stops should be listed in the correct order | Not Executed | Not Executed
TC-141 | M11 Journey Planning | Verify route details and timing | Verify route details and timing information | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open route details 3. Observe duration/timing 4. Compare with known data | Route and timing information should be consistent | Not Executed | Not Executed
TC-142 | M11 Journey Planning | Verify route refresh | Verify refresh in journey results | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Search a route 3. Refresh the results 4. Observe | Results should refresh without crash | Not Executed | Not Executed
TC-143 | M11 Journey Planning | Verify journey with GPS | Verify journey planning with 'current location' as source | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn ON location 3. Choose current location as source 4. Plan a route | Current location should be used as the source correctly | Not Executed | Not Executed
TC-144 | M11 Journey Planning | Verify journey without network | Verify journey planning with no Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Plan a route 4. Observe | Clear error message without crash | Not Executed | Not Executed
TC-145 | M11 Journey Planning | Verify journey Back button | Verify Back from route results/details | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Plan a route 3. Open details 4. Press Back | Back should return to the previous screen retaining inputs | Not Executed | Not Executed
TC-146 | M11 Journey Planning | Verify long route | Verify long routes with many stops | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select far-apart stops 3. Open route details 4. Scroll | Route should be displayed completely and be scrollable | Not Executed | Not Executed
TC-147 | M11 Journey Planning | Verify incorrect route data | Verify that route data is consistent with real routes | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Pick a route 3. Compare against official VVMT route information | Route data should match official data; mismatches documented | Not Executed | Not Executed
TC-148 | M12 Ticket Booking | Verify ticket feature availability | Verify whether ticket booking exists in the application | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Launch the app 3. Look for a ticket/pass option 4. Open it if present | If present proceed; otherwise mark all ticket cases NOT APPLICABLE | Not Executed | Not Executed
TC-149 | M12 Ticket Booking | Verify ticket selection | Verify that a ticket type can be selected | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the ticket feature 3. Select a ticket type | Selected ticket type should be highlighted/applied; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-150 | M12 Ticket Booking | Verify source selection | Verify source selection for ticket | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open ticket booking 3. Select source | Source should be selected and displayed; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-151 | M12 Ticket Booking | Verify destination selection | Verify destination selection for ticket | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open ticket booking 3. Select destination | Destination should be selected and displayed; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-152 | M12 Ticket Booking | Verify fare calculation | Verify fare for a source/destination | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select source and destination 3. Observe the fare 4. Compare with official fare chart | Fare should match the official fare; Requirement Confirmation Required | Not Executed | Not Executed
TC-153 | M12 Ticket Booking | Verify ticket quantity | Verify changing the ticket quantity | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Increase and decrease quantity 3. Observe fare update | Fare should update correctly; limits: Requirement Confirmation Required | Not Executed | Not Executed
TC-154 | M12 Ticket Booking | Verify valid ticket booking | Verify booking with valid data | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select valid details 3. Confirm 4. Observe result | Ticket should be generated successfully; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-155 | M12 Ticket Booking | Verify invalid ticket booking | Verify booking with invalid data | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enter invalid combination 3. Attempt to confirm | Validation message should be displayed; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-156 | M12 Ticket Booking | Verify empty fields | Verify booking with empty mandatory fields | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Leave source/destination empty 3. Tap confirm | Validation message should be displayed; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-157 | M12 Ticket Booking | Verify booking confirmation | Verify the confirmation screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete a booking 3. Observe confirmation | Confirmation with correct details should be displayed; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-158 | M12 Ticket Booking | Verify ticket generation | Verify the generated ticket content | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the generated ticket 3. Verify fields | Ticket should contain correct source, destination, fare, date/time; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-159 | M12 Ticket Booking | Verify duplicate ticket | Verify behaviour on repeated booking taps | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap confirm multiple times quickly 3. Check tickets generated | Only one ticket should be generated per confirmed booking; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-160 | M12 Ticket Booking | Verify ticket cancellation | Verify cancellation if supported | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a ticket 3. Look for cancel option 4. Cancel | Cancellation should work as per rules; if unsupported mark NOT APPLICABLE | Not Executed | Not Executed
TC-161 | M12 Ticket Booking | Verify ticket history | Verify ticket history list | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open ticket history 3. Observe entries | Previous tickets should be listed correctly; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-162 | M12 Ticket Booking | Verify ticket details | Verify details of a past ticket | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a ticket from history 3. Verify details | Details should match the booked ticket; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-163 | M12 Ticket Booking | Verify QR ticket | Verify QR/digital ticket display | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a ticket 3. Observe QR/barcode | QR should be displayed clearly if available; otherwise NOT APPLICABLE | Not Executed | Not Executed
TC-164 | M12 Ticket Booking | Verify ticket after app restart | Verify the ticket after restarting the app | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Generate a ticket 3. Close and relaunch the app 4. Open the ticket | Ticket should remain available; if the Ticket Booking feature does not exist mark NOT APPLICABLE | Not Executed | Not Executed
TC-165 | M13 Payment | Verify payment availability | Verify whether payment functionality exists | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Explore the app for payment options 3. Open payment screen if present | If payment exists proceed; otherwise mark payment cases NOT APPLICABLE | Not Executed | Not Executed
TC-166 | M13 Payment | Verify successful payment | Verify a successful payment flow (test mode/low-value only if safe) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start a booking 3. Proceed to payment 4. Complete payment | Payment should succeed and status should be displayed; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-167 | M13 Payment | Verify failed payment | Verify behaviour for failed payment | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Simulate failure (invalid/insufficient method in test mode) | Failure message should be displayed; no ticket issued; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-168 | M13 Payment | Verify cancelled payment | Verify behaviour when payment is cancelled | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Cancel on the payment screen | User should return safely with no charge/ticket; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-169 | M13 Payment | Verify payment timeout | Verify behaviour on payment timeout | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Wait without action | Timeout message should be displayed; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-170 | M13 Payment | Verify network interruption during payment | Verify behaviour if Internet drops mid payment | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Turn OFF Internet 4. Observe 5. Turn ON Internet | Clear status shown; no duplicate/uncertain charge; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-171 | M13 Payment | Verify Back button during payment | Verify Back button on payment screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Press Back 4. Observe | Confirmation or safe exit; no crash; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-172 | M13 Payment | Verify duplicate payment | Verify protection against duplicate payment | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap pay repeatedly 3. Check status | Only one payment should be processed; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-173 | M13 Payment | Verify payment status | Verify the payment status screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete a payment 3. Observe status | Correct status should be displayed; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-174 | M13 Payment | Verify ticket generation after payment | Verify ticket after successful payment | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete payment 3. Check tickets | Ticket should be generated after success only; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-175 | M13 Payment | Verify payment history | Verify payment history | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open payment history 3. Observe entries | History should list payments correctly; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-176 | M13 Payment | Verify app crash during payment | Verify recovery after app is closed during payment | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start payment 3. Force close the app 4. Reopen and check status | Payment/ticket status should be consistent; applicable only if payment exists, otherwise NOT APPLICABLE. Do not perform real financial transactions unless safe and appropriate | Not Executed | Not Executed
TC-177 | M14 Jobs | Verify Jobs page loading | Verify that the Jobs page loads | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the Jobs section 3. Wait for load 4. Observe | Page should load without crash | Not Executed | Not Executed
TC-178 | M14 Jobs | Verify Jobs empty state | Verify the Jobs page when no jobs are shown | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Jobs 3. Observe the screen 4. Check for message/blank | If no jobs exist, a clear 'No jobs available' type message should be displayed; blank screen without message is a potential UI/UX defect | Exploratory observation (formal execution pending): Jobs section did not show any jobs. Presence/absence of empty-state message to be recorded. | Not Executed
TC-179 | M14 Jobs | Verify 'No jobs' message | Verify the wording and visibility of the no-jobs message | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Jobs when empty 3. Read the message | Message should be clear and readable | Not Executed | Not Executed
TC-180 | M14 Jobs | Verify job listing | Verify job listing display (if jobs are available) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Jobs when jobs exist 3. Observe list | Jobs should be listed with titles | Not Executed | Not Executed
TC-181 | M14 Jobs | Verify job details | Verify job details (if jobs are available) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a job 3. Read the details | Details should be complete | Not Executed | Not Executed
TC-182 | M14 Jobs | Verify Jobs search | Verify search in Jobs if available | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Look for Jobs search 3. Search a keyword | Relevant jobs shown; if absent NOT APPLICABLE | Not Executed | Not Executed
TC-183 | M14 Jobs | Verify Jobs filter | Verify filters if available | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Look for filter 3. Apply a filter | Results filtered; if absent NOT APPLICABLE | Not Executed | Not Executed
TC-184 | M14 Jobs | Verify Apply button | Verify Apply action if available | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a job 3. Tap Apply | Apply should work or redirect; if absent NOT APPLICABLE | Not Executed | Not Executed
TC-185 | M14 Jobs | Verify Jobs with network failure | Verify Jobs behaviour without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open Jobs 4. Observe | Error/empty message should be shown; no crash | Not Executed | Not Executed
TC-186 | M14 Jobs | Verify Jobs refresh/back | Verify refresh and Back in Jobs | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Jobs 3. Refresh 4. Press Back | Refresh works and Back returns safely | Not Executed | Not Executed
TC-187 | M15 Games | Verify games list | Verify that the games list is displayed | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open Games 3. Observe the list | Available games should be listed | Exploratory observation (formal execution pending): Multiple games are available. | Not Executed
TC-188 | M15 Games | Verify game loading | Verify that a game loads | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a game 3. Observe loading | Game should load without crash | Not Executed | Not Executed
TC-189 | M15 Games | Verify game start | Verify that a game starts | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Load a game 3. Tap Start/Play | Game should begin | Not Executed | Not Executed
TC-190 | M15 Games | Verify game controls | Verify that controls respond | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play a game 3. Use all available controls | Controls should respond accurately | Not Executed | Not Executed
TC-191 | M15 Games | Verify level progression | Verify progression to the next level | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete level 1 3. Observe next level | Next level should unlock/start | Not Executed | Not Executed
TC-192 | M15 Games | Verify level completion | Verify the level completion screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete a level 3. Observe the screen | Completion feedback should be displayed | Not Executed | Not Executed
TC-193 | M15 Games | Verify score | Verify score updates | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play a game 3. Observe score | Score should update correctly | Not Executed | Not Executed
TC-194 | M15 Games | Verify progress persistence after refresh | Verify that completed level persists after refresh | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete a level 3. Refresh the game 4. Observe the level | Completed progress should persist if persistence is intended; Requirement Confirmation Required | Exploratory observation (formal execution pending): Previously completed level remained after refresh. Intent of persistence not confirmed. | Not Executed
TC-195 | M15 Games | Verify exit confirmation | Verify the exit confirmation when pressing Back during a game | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start a game 3. Press Back 4. Observe the dialog | An exit confirmation with Cancel and Exit options should be displayed | Back navigation displayed an exit confirmation containing Cancel and Exit options. | PASS
TC-196 | M15 Games | Verify cancel exit | Verify that Cancel keeps the user in the game | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Press Back in a game 3. Tap Cancel 4. Observe | Game should continue | Not Executed | Not Executed
TC-197 | M15 Games | Verify confirm exit | Verify that Exit leaves the game | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Press Back in a game 3. Tap Exit 4. Observe | User should return to the previous screen | Not Executed | Not Executed
TC-198 | M15 Games | Verify progress after app restart | Verify game progress after closing the app | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Complete a level 3. Close and reopen the app 4. Open the game | Progress should persist if intended; Requirement Confirmation Required | Not Executed | Not Executed
TC-199 | M15 Games | Verify game audio | Verify audio during gameplay and level completion | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play with volume up 3. Complete a level 4. Listen | Audio/music should play correctly | Exploratory observation (formal execution pending): Audio/music can be heard during gameplay/after levels. | Not Executed
TC-200 | M15 Games | Verify mute | Verify muting behaviour | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Mute the device/in-game audio 3. Play 4. Observe | No sound should play when muted | Not Executed | Not Executed
TC-201 | M15 Games | Verify advertisement display | Verify that advertisements are displayed during games | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play a game 3. Complete levels 4. Observe ads | Ads display correctly and do not crash the app | Exploratory observation (formal execution pending): Ads appear while playing and can appear after levels. Ads are not treated as defects by themselves. | Not Executed
TC-202 | M15 Games | Verify advertisement close | Verify closing an advertisement | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. When an ad appears 3. Close it 4. Observe | Ad should close and return to the game | Not Executed | Not Executed
TC-203 | M15 Games | Verify repeated advertisements | Verify the frequency of ads | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Close an ad 3. Observe if another ad appears 4. Count ads in 10 minutes | Ad frequency should be acceptable and not disrupt gameplay; acceptable frequency: Requirement Confirmation Required | Exploratory observation (formal execution pending): After closing/canceling an ad, another ad may appear. Impact on usability to be assessed. | Not Executed
TC-204 | M15 Games | Verify game lag | Verify game performance during gameplay | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play for 10 minutes 3. Observe lag/stutter 4. Record when it occurs | Game should run smoothly; performance expectation: Requirement Confirmation Required | Exploratory observation (formal execution pending): Game can become laggy. Needs investigation as a potential performance issue. | Not Executed
TC-205 | M15 Games | Verify game crash | Verify stability during long play | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play for 20 minutes 3. Switch levels 4. Observe crash | Game should not crash | Not Executed | Not Executed
TC-206 | M15 Games | Verify game restart | Verify restarting a game | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Play a game 3. Restart 4. Observe | Game should restart correctly | Not Executed | Not Executed
TC-207 | M15 Games | Verify game under network conditions | Verify games on slow/no network | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open a game 4. Play | Game behaviour should be recorded; Requirement Confirmation Required | Not Executed | Not Executed
TC-208 | M16 Network Testing | Verify behaviour on 4G | Verify application on 4G | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable 4G only 3. Use search, map, stops | App should function normally | Not Executed | Not Executed
TC-209 | M16 Network Testing | Verify behaviour on Wi-Fi | Verify application on Wi-Fi | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable Wi-Fi only 3. Use main features | App should function normally | Not Executed | Not Executed
TC-210 | M16 Network Testing | Verify behaviour with no Internet | Verify behaviour when no Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF data and Wi-Fi 3. Open the app and features | Clear messages or cached data without crash | Not Executed | Not Executed
TC-211 | M16 Network Testing | Verify network switching | Verify switching 4G to Wi-Fi | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use the map on 4G 3. Switch to Wi-Fi 4. Observe | App should continue without crash | Not Executed | Not Executed
TC-212 | M16 Network Testing | Verify slow network | Verify slow network (e.g. throttled) | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use a slow connection 3. Open map and search | App should show loading and remain stable | Not Executed | Not Executed
TC-213 | M16 Network Testing | Verify network interruption | Verify interruption mid action | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start a search 3. Turn OFF Internet 4. Observe | Clear error/message; no crash | Not Executed | Not Executed
TC-214 | M16 Network Testing | Verify network recovery | Verify recovery after Internet returns | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Use the app 4. Turn ON Internet 5. Observe | App should recover and refresh data | Not Executed | Not Executed
TC-215 | M16 Network Testing | Verify app launch without Internet | Verify cold launch without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Force stop 3. Turn OFF Internet 4. Launch | Behaviour recorded; Requirement Confirmation Required | Not Executed | Not Executed
TC-216 | M16 Network Testing | Verify search without Internet | Verify search without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Search bus/stop | Message or cached results; Requirement Confirmation Required | Not Executed | Not Executed
TC-217 | M16 Network Testing | Verify map without Internet | Verify map without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Turn OFF Internet 4. Observe | Behaviour recorded; Requirement Confirmation Required | Not Executed | Not Executed
TC-218 | M16 Network Testing | Verify bus tracking without Internet | Verify tracking when Internet is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open tracking 3. Turn OFF Internet 4. Observe | Updates stop or message shown; Requirement Confirmation Required | Not Executed | Not Executed
TC-219 | M16 Network Testing | Verify bus stop without Internet | Verify stops without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open a stop | Message or cached content; Requirement Confirmation Required | Not Executed | Not Executed
TC-220 | M16 Network Testing | Verify ticket without Internet | Verify tickets without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open the tickets feature | Behaviour recorded; NOT APPLICABLE if ticket absent | Not Executed | Not Executed
TC-221 | M16 Network Testing | Verify game without Internet | Verify games without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open a game | Behaviour recorded; Requirement Confirmation Required | Not Executed | Not Executed
TC-222 | M16 Network Testing | Verify Jobs without Internet | Verify Jobs without Internet | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Turn OFF Internet 3. Open Jobs | Error/empty message; no crash | Not Executed | Not Executed
TC-223 | M16 Network Testing | Verify cached vs static vs live data | Determine the nature of bus information visible after Internet is OFF | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Load buses on the map 3. Turn OFF Internet 4. Observe icons for 5 minutes 5. Turn ON Internet 6. Compare position changes | Data should be identified as cached, static, previously loaded or still updating; Requirement Confirmation Required | Exploratory observation (formal execution pending): Bus information can remain visible after network is turned OFF. Not yet classified as cached/static/live. | Not Executed
TC-224 | M17 UI / UX Testing | Verify alignment | Verify alignment of elements | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open all main screens 3. Observe alignment | Elements should be aligned | Not Executed | Not Executed
TC-225 | M17 UI / UX Testing | Verify buttons | Verify button appearance and state | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open screens 3. Observe buttons | Buttons should be visible and consistent | Not Executed | Not Executed
TC-226 | M17 UI / UX Testing | Verify fonts | Verify font consistency and size | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open screens 3. Observe fonts | Fonts should be consistent and readable | Not Executed | Not Executed
TC-227 | M17 UI / UX Testing | Verify text visibility | Verify contrast and visibility | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open screens in daylight/dark 3. Read | Text should be clearly readable | Not Executed | Not Executed
TC-228 | M17 UI / UX Testing | Verify icons | Verify icon clarity | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Observe icons | Icons should be clear and meaningful | Not Executed | Not Executed
TC-229 | M17 UI / UX Testing | Verify spacing | Verify spacing and padding | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Observe screens | Spacing should be consistent | Not Executed | Not Executed
TC-230 | M17 UI / UX Testing | Verify screen responsiveness | Verify layout fits the screen | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open screens 3. Scroll 4. Observe | No cut-off/overlap | Not Executed | Not Executed
TC-231 | M17 UI / UX Testing | Verify map layout usable space | Verify that the map provides sufficient usable space with route/bus stop panels visible | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map for a bus (e.g. '202 to Vasai Phata') 3. Observe the proportion occupied by the info panel 4. Try to pan/zoom 5. Collapse/expand the panel if possible 6. Assess visibility of the route | Map area should be sufficient for use; panel size should not obstruct map interaction; usability impact must be confirmed before reporting | Exploratory observation (formal execution pending): Route/bus-stop information such as '202 to Vasai Phata' occupies a large portion of the screen. Usability impact not yet confirmed. | Not Executed
TC-232 | M17 UI / UX Testing | Verify bottom panels | Verify bottom panel behaviour | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open the map 3. Drag/tap the bottom panel | Panel should open/close smoothly | Not Executed | Not Executed
TC-233 | M17 UI / UX Testing | Verify bus information display | Verify bus info layout | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap a bus 3. Observe the info | Information should be readable | Not Executed | Not Executed
TC-234 | M17 UI / UX Testing | Verify bus stop information display | Verify stop info layout | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open a stop 3. Observe info | Information should be readable | Not Executed | Not Executed
TC-235 | M17 UI / UX Testing | Verify empty screens | Verify empty-state messages | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open screens with no data 3. Observe | Meaningful empty-state message | Not Executed | Not Executed
TC-236 | M17 UI / UX Testing | Verify blank screens | Verify no unexplained blank screens occur | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Navigate through all screens 3. Record any blank screen | No unexplained blank screens | Not Executed | Not Executed
TC-237 | M17 UI / UX Testing | Verify error messages | Verify clarity of error messages | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Trigger errors 3. Read messages | Messages should be clear and actionable | Not Executed | Not Executed
TC-238 | M17 UI / UX Testing | Verify loading indicators | Verify loading indicators | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open data screens 3. Observe | Loading indicator should appear during loading | Not Executed | Not Executed
TC-239 | M17 UI / UX Testing | Verify touch targets | Verify tap target size | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Tap small buttons/icons | Targets should be easily tappable | Not Executed | Not Executed
TC-240 | M17 UI / UX Testing | Verify navigation UI | Verify navigation controls | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use navigation elements | Controls should be intuitive and functional | Not Executed | Not Executed
TC-241 | M17 UI / UX Testing | Verify consistency | Verify UI consistency across modules | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Compare styles of screens | Consistent look and feel | Not Executed | Not Executed
TC-242 | M18 Compatibility Testing | Verify on different Android versions | Verify on multiple Android versions | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Install on devices with different Android versions 3. Run the smoke tests | App should work on supported versions; supported versions: Requirement Confirmation Required | Not Executed | Not Executed
TC-243 | M18 Compatibility Testing | Verify on different screen sizes | Verify on small and large screens | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Install on different screen sizes 3. Observe layouts | Layout should adapt | Not Executed | Not Executed
TC-244 | M18 Compatibility Testing | Verify on different resolutions | Verify different resolutions | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Run on HD/FHD+ devices 3. Observe | UI should be sharp and not distorted | Not Executed | Not Executed
TC-245 | M18 Compatibility Testing | Verify portrait mode | Verify portrait | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use the app in portrait | Layout should be correct | Not Executed | Not Executed
TC-246 | M18 Compatibility Testing | Verify landscape mode | Verify landscape if supported | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Rotate the device 3. Observe | Layout adapts or orientation locked; Requirement Confirmation Required | Not Executed | Not Executed
TC-247 | M18 Compatibility Testing | Verify different network conditions | Verify on varied networks | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Test on 4G, Wi-Fi, slow 3. Observe | App should work as per network | Not Executed | Not Executed
TC-248 | M18 Compatibility Testing | Verify low battery | Verify on low battery/battery saver | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Enable battery saver 3. Use tracking | App should work | Not Executed | Not Executed
TC-249 | M18 Compatibility Testing | Verify low storage | Verify on low storage | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Reduce free space 3. Launch | App should run without crash | Not Executed | Not Executed
TC-250 | M18 Compatibility Testing | Verify background/foreground | Verify background/foreground handling | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Switch apps repeatedly | App should resume | Not Executed | Not Executed
TC-251 | M18 Compatibility Testing | Verify phone rotation | Verify rotation during use | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Rotate on map/game 3. Observe | State should be retained | Not Executed | Not Executed
TC-252 | M19 Performance Observation (Manual) | Verify app launch time | Measure app launch time on 4G | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Close the app 3. Start the stopwatch and tap the icon 4. Stop when usable 5. Repeat 3 times | Launch time should be within the acceptable benchmark; benchmark: Requirement Confirmation Required | Application took approximately 10 seconds to become usable on 4G. (Observed; no benchmark defined, so not treated as a failure.) | Not Executed
TC-253 | M19 Performance Observation (Manual) | Verify screen loading time | Measure screen load time | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Open each main screen 3. Time loading | Screens should load reasonably; benchmark: Requirement Confirmation Required | Not Executed | Not Executed
TC-254 | M19 Performance Observation (Manual) | Verify map loading time | Measure map load time | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Select a bus 3. Time until the map is ready | Map should load in acceptable time; benchmark: Requirement Confirmation Required | Not Executed | Not Executed
TC-255 | M19 Performance Observation (Manual) | Verify search response time | Measure search response | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Search a bus 3. Time the result | Results should appear promptly; benchmark: Requirement Confirmation Required | Not Executed | Not Executed
TC-256 | M19 Performance Observation (Manual) | Verify bus tracking refresh time | Measure tracking refresh | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Observe icon refresh 3. Record intervals | Refresh should be regular; interval: Requirement Confirmation Required | Not Executed | Not Executed
TC-257 | M19 Performance Observation (Manual) | Verify game loading time | Measure game load | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Start games 3. Time loading | Game should load in reasonable time | Not Executed | Not Executed
TC-258 | M19 Performance Observation (Manual) | Verify UI responsiveness | Verify responsiveness | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Perform quick taps/scrolls | UI should respond immediately | Not Executed | Not Executed
TC-259 | M19 Performance Observation (Manual) | Verify freezing | Verify no freezing in extended use | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use app 20 minutes 3. Observe freezes | No freezing | Not Executed | Not Executed
TC-260 | M19 Performance Observation (Manual) | Verify crash in extended session | Verify stability | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use all modules for 30 minutes 3. Note crashes | No crash | Not Executed | Not Executed
TC-261 | M19 Performance Observation (Manual) | Verify battery/data usage | Observe battery and data usage | 1. Launch the Aapli Bus VVMT application (4G network, GPS ON unless stated otherwise) 2. Use app 15 minutes 3. Check usage | Usage should be reasonable; threshold: Requirement Confirmation Required | Not Executed | Not Executed

## Defect Report
BUG ID | TEST CASE ID | MODULE | DEFECT TITLE | DESCRIPTION | STEPS TO REPRODUCE | EXPECTED RESULT | ACTUAL RESULT | SEVERITY | PRIORITY | ENVIRONMENT | STATUS
APLI-001 | TC-117 | Bus Stops | Nalasopara Phata bus stop opens to a blank screen | Selecting 'Nalasopara Phata' opens a screen that appears blank without details or message. | 1. Launch the app 2. Open bus stop search 3. Select 'Nalasopara Phata' 4. Observe the screen | Relevant bus stop details should be displayed | Blank screen is displayed (observed during exploratory testing) | Major | High | [DEVICE] / [ANDROID VERSION] / 4G | Potential Defect - to be confirmed
APLI-002 | TC-111 | Location Accuracy | Possible incorrect location/area name displayed ('Polhar Highway Rasta') | App displayed 'Polhar Highway Rasta'; tester expected a name such as 'Pelhar / Vasai Phata'. Official name not verified. | 1. Enable location 2. Open the screen showing the area name 3. Note displayed name 4. Compare with official source | Displayed area name should match the officially verified name | Displayed 'Polhar Highway Rasta' | Minor | Medium | [DEVICE] / [ANDROID VERSION] / 4G | Requirement Confirmation Required - to be confirmed
APLI-003 | TC-035 | Localization | Announcement content does not change with selected language | UI/paragraph content changes but announcements appear unchanged. Whether announcements should be localized is unconfirmed. | 1. Open Announcements and note content 2. Change language 3. Reopen announcements 4. Compare | Announcement content should change if localization of announcements is expected | Announcement content did not appear to change | Minor | Medium | [DEVICE] / [ANDROID VERSION] / 4G | Potential Defect - to be confirmed
APLI-004 | TC-231 | UI / UX | Map UI may provide insufficient map area | Route/bus-stop info (e.g. '202 to Vasai Phata') occupies a large portion of the map screen. | 1. Search a bus (e.g. 202) 2. Open the map 3. Observe space used by the info panel 4. Try pan/zoom | Map should provide sufficient usable area | Info panel occupies a large portion of the screen | Minor | Medium | [DEVICE] / [ANDROID VERSION] / 4G | Requirement Confirmation Required - to be confirmed
APLI-005 | TC-120 | Bus Stops | 'See All' may display nearby bus stops rather than all bus stops | 'See All' shows nearby stops. Intended meaning unconfirmed. | 1. Open nearby bus stops 2. Tap See All 3. Observe list | 'See All' should match the defined meaning (all stops or all nearby stops) | Nearby bus stops are shown | Trivial | Low | [DEVICE] / [ANDROID VERSION] / 4G | Requirement Confirmation Required - to be confirmed
APLI-006 | TC-204 | Games | Game becomes laggy during gameplay | Lag observed during gameplay; conditions to be investigated. | 1. Open Games 2. Start a game 3. Play for several minutes 4. Observe lag | Game should run smoothly | Game became laggy | Minor | Medium | [DEVICE] / [ANDROID VERSION] / 4G | Potential Defect - to be confirmed
APLI-007 | TC-203 | Games | Repeated advertisements may negatively affect game usability | Another ad can appear after closing one, and ads appear after levels. Ads are not defects by themselves. | 1. Start a game 2. Complete levels 3. Close an ad 4. Observe if another appears | Ad frequency should not disrupt gameplay | Repeated ads observed | Minor | Low | [DEVICE] / [ANDROID VERSION] / 4G | Requirement Confirmation Required - to be confirmed
APLI-008 | TC-252 | Performance | Application takes approximately 10 seconds to launch on 4G | Launch took ~10 seconds on 4G; no benchmark defined. | 1. Close the app 2. Tap icon and start stopwatch 3. Stop when usable | Launch within acceptable benchmark (RC) | ~10 seconds to become usable | Minor | Medium | [DEVICE] / [ANDROID VERSION] / 4G | Performance Observation - to be confirmed

## RTM
REQUIREMENT ID | MODULE | REQUIREMENT | TEST CASE ID | TEST CASE DESCRIPTION | STATUS | DEFECT ID
REQ-001 | Installation & Launch | Application installs and launches successfully to a usable home screen | TC-001 to TC-006 | 6 case(s): application installation; application identity; first launch; ... | Not Executed | -
REQ-002 | Installation & Launch | Application remains stable (no crash/freeze) across restart and lifecycle events | TC-009 to TC-016 | 8 case(s): app restart; launch after force stop; background/foreground behaviour; ... | Not Executed | -
REQ-003 | Installation & Launch | Application launch behaviour under different Internet/GPS states | TC-007 to TC-008 | 2 case(s): launch without Internet; launch with GPS disabled | Not Executed | -
REQ-004 | Navigation | User can navigate between screens; back/forward/exit behave consistently | TC-017 to TC-026 | 10 case(s): home screen; navigation menu; Back button; ... | Not Executed | -
REQ-005 | Localization | UI text changes according to selected language | TC-027 to TC-034, TC-038 to TC-039 | 10 case(s): language change; UI translation; buttons translation; ... | Not Executed | -
REQ-006 | Localization | Language persistence and localization scope (including announcements) | TC-035 to TC-037 | 3 case(s): announcement localization; language persistence; language after device restart | Not Executed | APLI-003
REQ-007 | Announcements | Announcements can be listed, opened (eye/view button) and closed | TC-040 to TC-050 | 11 case(s): announcement list; announcement loading; eye/view button opens announcement; ... | Partially Executed (1/11 PASS) | -
REQ-008 | Bus Search | User can search a bus by number and see matching results | TC-051, TC-053, TC-060, TC-062 | 4 case(s): search by valid bus number; search for bus 107; multiple results; ... | Partially Executed (1/4 PASS) | -
REQ-009 | Bus Search | Search handles invalid, empty, partial and special input gracefully | TC-052, TC-054 to TC-059, TC-063 to TC-065 | 10 case(s): search by invalid bus number; empty search; partial bus number; ... | Not Executed | -
REQ-010 | Bus Search | User can search bus stops and select a result | TC-061, TC-115 to TC-116 | 3 case(s): bus stop search; bus stop search; bus stop selection | Partially Executed (1/3 PASS) | -
REQ-011 | Bus Details & Map | Selecting a bus opens a map with route and bus information | TC-066 to TC-072, TC-080 | 8 case(s): selecting a bus opens map; map loading; bus icon display; ... | Partially Executed (3/8 PASS) | -
REQ-012 | Bus Details & Map | Map supports zoom/pan/refresh and shows bus stops and route | TC-073 to TC-079 | 7 case(s): map zoom; map movement; map refresh; ... | Not Executed | -
REQ-013 | Live Tracking | Bus location/movement/status is displayed and updated on the map | TC-081 to TC-084, TC-086 to TC-094 | 13 case(s): bus location display; bus movement; bus status; ... | Not Executed | -
REQ-014 | Live Tracking | Bus colour indicators correspond to the status defined by the application | TC-085 | 1 case(s): bus colour indicators | Not Executed | -
REQ-015 | GPS / Location | Location permission flow (allow/deny/revoke) works correctly | TC-095 to TC-096, TC-099 to TC-101 | 5 case(s): location permission allowed; location permission denied; first permission request; ... | Not Executed | -
REQ-016 | GPS / Location | Application behaviour when device location is ON/OFF | TC-097 to TC-098, TC-107 to TC-110 | 6 case(s): location disabled; location enabled; buses visible with location OFF - previously loaded data; ... | Not Executed | -
REQ-017 | GPS / Location | Nearby buses/bus stops are shown based on user location | TC-102 to TC-106, TC-119 | 6 case(s): current location; nearby bus stops; nearby buses; ... | Not Executed | -
REQ-018 | Location Accuracy | Displayed location/area name is accurate | TC-111 to TC-114 | 4 case(s): accuracy of displayed location/area name; location name against official source; location name consistency across screens; ... | Not Executed | APLI-002
REQ-019 | Bus Stops | Bus stop opens and shows relevant stop details and routes | TC-117 to TC-118, TC-122 to TC-130 | 11 case(s): Nalasopara Phata bus stop opens correctly; bus stop details; bus stop map; ... | Not Executed | APLI-001
REQ-020 | Bus Stops | 'See All' behaviour (all stops vs nearby stops) | TC-120 to TC-121 | 2 case(s): 'See All' meaning; 'See All' list completeness | Not Executed | APLI-005
REQ-021 | Journey Planning | User can plan a journey between source and destination (if feature exists) | TC-131 to TC-147 | 17 case(s): journey planning availability; source selection; destination selection; ... | Not Executed | -
REQ-022 | Ticket Booking | User can select and generate a ticket (if feature exists) | TC-148 to TC-160 | 13 case(s): ticket feature availability; ticket selection; source selection; ... | Not Executed | -
REQ-023 | Ticket Booking | Ticket history/details/digital ticket display (if feature exists) | TC-161 to TC-164 | 4 case(s): ticket history; ticket details; QR ticket; ... | Not Executed | -
REQ-024 | Payment | Payment success/failure/cancel handling (if feature exists) | TC-165 to TC-176 | 12 case(s): payment availability; successful payment; failed payment; ... | Not Executed | -
REQ-025 | Jobs | Jobs section shows listings or an appropriate empty state | TC-177 to TC-186 | 10 case(s): Jobs page loading; Jobs empty state; 'No jobs' message; ... | Not Executed | -
REQ-026 | Games | Games can be listed, launched and played | TC-187 to TC-193, TC-204 to TC-207 | 11 case(s): games list; game loading; game start; ... | Not Executed | APLI-006
REQ-027 | Games | Game progress persistence and exit confirmation | TC-194 to TC-198 | 5 case(s): progress persistence after refresh; exit confirmation; cancel exit; ... | Partially Executed (1/5 PASS) | -
REQ-028 | Games | Advertisement behaviour during gameplay | TC-201 to TC-203 | 3 case(s): advertisement display; advertisement close; repeated advertisements | Not Executed | APLI-007
REQ-029 | Games | Game audio and mute behaviour | TC-199 to TC-200 | 2 case(s): game audio; mute | Not Executed | -
REQ-030 | Network | Application behaviour across 4G / Wi-Fi / no Internet / switching | TC-208 to TC-214 | 7 case(s): behaviour on 4G; behaviour on Wi-Fi; behaviour with no Internet; ... | Not Executed | -
REQ-031 | Network | Offline behaviour: cached vs static vs live data | TC-215 to TC-223 | 9 case(s): app launch without Internet; search without Internet; map without Internet; ... | Not Executed | -
REQ-032 | UI / UX | UI elements are aligned, readable and consistent | TC-224 to TC-230, TC-232 to TC-234, TC-239 to TC-241 | 13 case(s): alignment; buttons; fonts; ... | Not Executed | -
REQ-033 | UI / UX | Loading, empty, blank and error states give proper feedback | TC-235 to TC-238 | 4 case(s): empty screens; blank screens; error messages; ... | Not Executed | -
REQ-034 | UI / UX | Map screen provides sufficient usable map area | TC-231 | 1 case(s): map layout usable space | Not Executed | APLI-004
REQ-035 | Compatibility | Application works across Android versions, screen sizes and device conditions | TC-242 to TC-251 | 10 case(s): on different Android versions; on different screen sizes; on different resolutions; ... | Not Executed | -
REQ-036 | Performance | Manual observation of launch, load, response and stability | TC-252 to TC-261 | 10 case(s): app launch time; screen loading time; map loading time; ... | Not Executed | APLI-008

## Observations
OBSERVATION ID | MODULE | OBSERVATION | ACTION TAKEN | RESULT | DEFECT?
OBS-001 | Performance | App launch took approximately 10 seconds on 4G | Measured launch time | ~10 seconds to usable state | Performance Observation (APLI-008)
OBS-002 | Announcements | Announcement opens using the eye/view button | Tapped eye/view button | Announcement opened | No
OBS-003 | Bus Search | Buses 101-106 were available | Searched buses | Buses found | No
OBS-004 | Bus Search | Bus 107 not found | Searched 107 | Not found | Requirement Confirmation Required
OBS-005 | Bus Details & Map | Bus 102 opens map | Searched and selected Bus 102 | Map opened | No
OBS-006 | Bus Details & Map | Bus icons appear on map | Viewed the route | Icons visible | No
OBS-007 | Bus Details & Map | Tapping bus icon displays bus number | Tapped a bus icon | Number/details displayed | No
OBS-008 | Live Tracking | Green/yellow bus indicators observed (a yellow bus appeared moving) | Observed map | Colours seen; meaning unconfirmed | Requirement Confirmation Required
OBS-009 | Bus Stops | Bus stops can be searched | Searched stops | Stops searchable | No
OBS-010 | Location Accuracy | Location name displayed as 'Polhar Highway Rasta' | Compared with expectation | Name possibly inaccurate; unverified | Requirement Confirmation Required (APLI-002)
OBS-011 | GPS / Location | Buses remain visible when device location is OFF | Turned OFF location | Buses still visible | Requirement Confirmation Required
OBS-012 | Network | Bus information can remain visible when network is OFF | Turned OFF network | Information still visible | Requirement Confirmation Required
OBS-013 | Installation & Launch | Internet appears necessary during initial app opening | Opened app without Internet | Internet appears needed at initial open | Requirement Confirmation Required
OBS-014 | Localization | UI language changes | Changed language | UI text changed | No
OBS-015 | Localization | Announcement content does not appear to change with language | Changed language and viewed announcements | Announcement content unchanged | Potential Defect / Requirement Confirmation Required (APLI-003)
OBS-016 | Jobs | Jobs section had no visible jobs | Opened Jobs | No jobs shown | Requirement Confirmation Required
OBS-017 | Games | Multiple games are available | Opened Games | Several games listed | No
OBS-018 | Games | Multiple/repeated ads can appear | Played games | Ads appeared repeatedly | Requirement Confirmation Required (APLI-007)
OBS-019 | Games | Game can become laggy | Played games | Lag noticed | Potential Defect (APLI-006)
OBS-020 | Games | Game progress remains after refresh | Refreshed game | Progress remained | Requirement Confirmation Required
OBS-021 | Games | Back button displays game exit confirmation | Pressed Back in game | Exit confirmation (Cancel/Exit) shown | No
OBS-022 | Bus Stops | Nalasopara Phata opens blank | Opened the stop | Blank screen | Potential Defect (APLI-001)
OBS-023 | Bus Stops | 'See All' shows nearby bus stops | Tapped See All | Nearby stops shown | Requirement Confirmation Required (APLI-005)
OBS-024 | UI / UX | Map info panel occupies large screen portion | Viewed map | Large portion occupied | Requirement Confirmation Required (APLI-004)

## Execution Summary
METRIC | VALUE
Total Test Cases
Passed
Failed
Blocked
Not Executed
Not Applicable
Executed
Confirmed Defects | 0
Potential Defects | 8